Hurricane Erick and Tropical Storm Flossie were two of the stronger storms to enter the Central Pacific in 2019 but did not directly impact Hawaii./NOAA

(USGS photo)

Volcanos

Hurricane Erick and Tropical Storm Flossie were two of the stronger storms to enter the Central Pacific in 2019 but did not directly impact Hawaii./NOAA

(USGS photo)

Volcanos

# State of Hawai‘i

# Hawai‘i Emergency Management Agency

## Multi-Year Training and Exercise Plan

2020-2022 (January 2020)

# State of Hawai‘i

# Hawai‘i Emergency Management Agency

## Multi-Year Training and Exercise Plan

2020-2022 (January 2020)                                                                              Approved by HI-EMA Executive Officer, Luke Meyers

Senior Leaders discusses during the 2019 Makani Pahili Exercise Executive Education Seminar. (State of Hawaii photo)

State of Hawai‘iSenior Leaders discussing during the 2019 Makani Pahili Exercise Executive Education Seminar. (State of Hawaii photo)

A wildfire in West Maui in July 2019 forced thousands of residents to evacuate. (County of Maui photo)

A wildfire in West Maui in July 2019 forced thousands of residents to evacuate. (County of Maui photo)

# Approved by HI-EMA Administrator, Luke Meyers as of May 12, 2020

This page intentionally left blank.

# Preface

The State of Hawai‘i is especially vulnerable to natural disasters due to its unique geographical setting. That was never more evident than in 2018 when federal emergency and/or disaster declarations were approved for four events in four months as floods and landslides, a volcanic eruption and two hurricanes impacted the state.

The citizens of Hawai‘i have demonstrated remarkable resilience in the aftermath of these incidents and other previous disasters. The ever-present threat posed by a number of hazards, compounded by Hawai‘i’s remote geographic location, underscores the need for a comprehensive, all-hazards approach toward emergency preparedness and response.

The State of Hawai‘i, in its efforts to prevent, protect, mitigate against, respond to and recover from a broad range of natural and humane incidents, has embraced a capabilities-based approach to training and exercising.  As part of this approach, Hawai‘i has identified a need to coordinate planning, training, and exercising to strengthen overall proficiency in executing the 32 “core capabilities” defined in the National Preparedness Goal. Training and exercising play a crucial role in this process and provide Hawai‘i with a strategy for attaining, practicing, validating and improving new capabilities.

The Multi-Year Training and Exercise Plan (TEP) is shaped by input from stakeholders across all levels of government, the private sector and non-governmental organizations. It reflects the state’s commitment to providing a culture that promotes continuous learning and improvement.

The TEP is a product of the Hawai‘i Emergency Management Agency (HI-EMA) and the state’s Office of Homeland Security (OHS). The mission of the Hawai‘i Emergency Management Agency is to institute training, preparedness and public-information programs in coordination with the state, counties, the federal government, other states and private-sector and nonprofit organization. (Hawai‘i Revised Statutes 127A).  The training mission of the state’s OHS is to provide programs, in coordination with county agencies, other state and federal agencies, and the private sector, to educate and train publicly and privately employed workers and the general public to be prepared for potential attacks. (Hawai‘i Revised Statutes 128A-1).

# Points of Contact (POCs)

David A. Lopez

Executive Officer

Hawai‘i Emergency Management Agency

3949 Diamond Head Road

Honolulu, HI 96816

808-733-4300, ext. 521 (office)

david.a.lopez@hawaii.gov

Lalo Medina

Acting Preparedness Branch Chief/Exercise Officer

Hawai‘i Emergency Management Agency

3949 Diamond Head Road

Honolulu, HI 96815

808-733-4300 x523 (office)

eulalio.medina@hawaii.gov

Niea Gardner

Training Officer

Hawai‘i Emergency Management Agency

3949 Diamond Head Road

Honolulu, HI 96815

808-733-4300 x621 (office)

hyniea.l.gardner@hawaii.gov

Dee Cook (Homeland Security-funded trainings)

Administrator

Office of Homeland Security

3949 Diamond Head Road

Honolulu, HI 96816

dolores.m.cook@hawaii.gov

Colby Stanton

Director of Readiness

Pacific Area Office (PAO)

FEMA Region IX

Fort Shafter, Hawaii

808-851-7918 (Office)

colby.stanton@fema.dhs.gov

# Table of Contents

State of Hawai‘i	ii

Hawai‘i Emergency Management Agency	ii

Preface	iv

Points of Contact (POCs)	v

Table of Contents	1

Purpose	2

Methodology	3

Training and Exercise Program Priorities	4

Critical Transportation	6

State Agency Readiness	7

Mass Care/Logistics & Supply Chain Management	10

Housing	11

Protection Mission Area	12

Multi-year Training and Exercise Schedule	16

Acknowledgements	28

Maintenance Section	28

# Purpose

“A secure and resilient nation with the capabilities required across the whole community to prevent, protect against, mitigate, respond to, and recover from the threats and hazards that pose the greatest risk.”

- National Preparedness Goal

The purpose of the Multi-year Training and Exercise Plan (TEP) is to document the state’s overall training and exercise program priorities. These priorities are linked to core capabilities essential to achieving the National Preparedness Goal, and are informed by the State of Threat and Hazard Identification and Risk Analysis (THIRA)/Stakeholder Preparedness Review (SPR), After-Action Reports/Improvement Plans, the Training and Exercise Planning Workshop (TEPW), and other requirements set forth by senior leadership, statute and grant guidance.

The Multi-year TEP lays out a combination of progressively building exercises – along with the associated training requirements – which address the priorities identified throughout the year. A progressive, multi-year exercise program enables organizations to participate in a series of increasingly complex exercises, with each successive exercise building upon the previous one until mastery is achieved. Further, by including training requirements in the planning process, our organization can address known shortfalls prior to exercising capabilities.

Included in this Multi-year TEP is a training and exercise schedule, which provides a listing of proposed activities scheduled for the calendar years 2020 through 2022.

# Methodology

- The following sources were used to help identify risks and establish priorities for this TEP include the following:

2018 Hawai‘i State Hazard Mitigation Plan (SHMP)

- The SHMP identifies the major natural hazards that affect our state, assesses the risk that each hazard poses, analyzes the vulnerability of our people, property and infrastructure to the specific hazard, and recommends actions that can be taken to reduce the risk and vulnerability to the hazard.

2018 Threat and Hazard Identification and Risk Assessment and Stakeholder Preparedness Review (THIRA/SPR)

- The THIRA/SPR identifies hazards of greatest concern to the state, assesses the state’s capabilities to address those hazards, identifies gaps and strategies for addressing those gaps.

2018 Hawai‘i Joint Counterterrorism Awareness Workshop Series (JCTAWS)

- JCTAWS is a nationwide initiative designed to improve the ability of local jurisdictions to prepare for, protect against, and respond to complex terrorist attacks.

- After-Action Report/Improvement Plan (AAR/IP): 2018 Disasters

A consolidated AAR/IP was produced for the state response to the 2019 disasters including the April 2018 floods, the May 2018 Kīlauea Eruption and the responses to Hurricanes Lane and Olivia.

- Input from State of Hawai‘i Departments, county emergency management agencies and non-governmental partners through the Training and Exercise Planning Workshop.

- The purpose of the Emergency Management Performance Grant Program (EMPG) is to provide Federal funds to states to assist state, local, territorial and tribal governments in preparing for all hazards.

The state training and exercise program utilizes the Homeland Security and Exercise Evaluation Program (HSEEP) methodology and process to plan, develop and conduct all exercise and training.

## State Training and Exercise Planning Workshop (TEPW)

The TEP is a product of the Training and TEPW, which was hosted by the HI-EMA hosted on October 10, 2019. Participants included representatives from the state, county and federal agencies, as well as from nonprofit organizations and the private sector.

The sources above were presented to participants, as well as existing state emergency management and homeland security priorities. Group discussions were held to validate proposed training and exercise priorities and identify specific capability elements to sustain and build through the training and exercise programs.

TEPW participants then reviewed the schedule of planned training and exercises to de-conflict events.

Future TEPWs will be conducted on the 1st Quarter of the year (Jan-Mar), rather than the 4th Quarter of the year (Oct-Dec) due to continuous improvement of our training and exercise program. The next TEPW is scheduled for January 12, 2021.

# Training and Exercise Program Priorities

Identification of Program Priorities

The 2020 – 2022 Training and Exercise  Program priorities for the current training and exercise cycle were determined by the state and counties, and the supporting core capabilities are based on stakeholder input provided at the TEPW.  The priorities focus on threats and hazards from our State Threat and Hazard Identification and Risk Assessment (THIRA) and areas identified for improvement in After Action Reports/Improvement Plans (AAR/IPs) from real events and exercises. A Corrective Action Program (CAP) is being implemented that will track and validate corrective actions in future exercises. Grant funding requirements and other reports, such as the State Preparedness Report (SPR), were also considered when determining the program priorities.

Factors for Consideration in Developing Exercise Program Priorities

Program Priorities for the 2020 to 2022 Training and Exercise Cycle

The state’s priorities for training and exercise reflect core capabilities determined to present the greatest challenges to the state’s preparedness. In addition, the state has identified a set of core capabilities that are standing priorities for training and exercise due to their criticality across all mission areas and/or their importance to ensuring success in other capability areas.

Response Mission Area

- Critical Transportation

- Logistics and Supply Chain Management

- Mass Care Services

Recovery Mission Area

- Housing

Protection Mission Area

- Cybersecurity (Homeland Security)

- Physical Protective Measures (Homeland Security)

- Risk Management for Protection Programs and Activities (Homeland Security)

Common Core Capabilities

- Planning

- Operational Coordination

- Operational Communication

# Critical Transportation

The 2015 State of Hawai‘i Catastrophic Hurricane Annex and subsequent planning efforts during the last training and exercise cycle (2017-2019) to examine the state’s critical transportation systems and their dependencies, brought into sharp focus the magnitude of the logistical challenges the state will face following a major disaster. As a result, major planning initiatives are underway to address these issues and it is a priority of the training and exercise program to support the development of those plans.

| Debris Management | The training and exercise program will support statewide debris management planning. Debris management will be a focus of the state’s annual hurricane exercise for the 2020 – 2022 cycle. The debris management exercise objective is to develop a tactical debris management plan. In addition, mutually develop at the same time the state debris management operational support plan based on the anticipated requests or deficiencies identified in the county debris management tactical plans. |
| --- | --- |
| Port Restoration | Port restoration will be a focus of the state’s annual hurricane exercise for the 2020 – 2022 cycle. The port restoration exercise objective for 2020 is to develop a port restoration plan that has the capability to restore sea port operations at the Port of Honolulu. The state exercise objective is to develop a port restoration operational support plan that has the capability to restore sea port operations at the Port of Honolulu. The focus on sea port restoration will continue next year 2021 and expand to neighbor island commercial sea ports. |

## Rationale for Critical Transportation Focus

- Hawai‘i Emergency Management Agency Critical Systems Analysis (2016)

- State of Hawai‘i Hazard Mitigation Plan (2018)

- State of Hawai‘i Threat and Hazard Identification and Risk Assessment (2018)

- State and County debris plans

## Supporting Training

- Debris Management Planning Workshops (See Multi-year Training and Exercise Schedule)

- Port Restoration Planning Workshops (See Multi-year Training and Exercise Schedule)

## Supporting Exercises

- Debris Management Tabletop Exercise (See Multi-year Training and Exercise Schedule)

- State/C&C of Honolulu Port Restoration Tabletop Exercise (See Multi-year Training and Exercise Schedule)

# State Agency Readiness

On August 11, 2015, Gov. David Ige signed Administrative Directive No. 15-01, requiring each state agency and department in the Executive Branch to establish minimum emergency management requirements. An ongoing focus for the Hawai‘i Emergency Management Agency has been on providing training and exercise support to help departments meet these requirements and improve their readiness to execute their emergency and essential functions during a disaster requiring state support. Specifically, the training and exercise program seeks to increase the capabilities of state agencies in the areas of planning, operational coordination, situation assessment and operational communication.

| Continuity of Operations Planning | The Administrative Directive requires all state agencies to maintain a Departmental Emergency Operations Plan (EOP) and a Continuity of Operations Plan (COOP). While departments have made progress in developing EOPs, continuity planning remains a major gap. Continuity planning will be a priority for the training program, and the exercise program will focus on creating opportunities for departments to test and validate completed plans. |
| --- | --- |
| State Emergency Response Team Curriculum | The Administrative Directive requires each department to identify Emergency Management Officers (EMO) and State Emergency Support Function (SESF) representatives. These positions, along with HI-EMA staff, collectively make up the State Emergency Response Team (SERT). HI-EMA will sustain and continue to expand the SERT curriculum to ensure SERT members understand their roles and how they fit into state plans. The state will continue regular delivery of State Emergency Response Team (SERT) Orientation and WebEOC Training. New priorities include the development of training on State Emergency Response Function (SESF) roles, adding an emergency management component of new employee orientation statewide and drills to maintain familiarity with SEOC operations. |
| Senior Leader Role in Emergency Response/Recovery | Continue to educate the senior leadership in the Hawaiian Islands and potential members of the Unified Coordination Group on their role in a catastrophic incident and what types of challenges they can expect and decisions that they may have to make, by discussing selected critical issues i.e. post disaster housing and decision points. |

## Corresponding Core Capabilities

- Planning

- Operational Coordination

- Operational Communication

- Situation Assessment

## Rationale for Focus on State Agency Readiness

- Administrative Directive No. 15-01 https://dod.hawaii.gov/hiema/files/2017/08/AD-15-01-Emergency-Management-Preparedness-Requirements-for-Departments.pdf

- State of Hawai‘i Threat and Hazard Identification and Risk Assessment (2018)

- HI-EMA Training Survey (October 2016)

- State of Hawai‘i Emergency Operations Plan (May 2017)

- After-Action Report/Improvement Plan (AAR/IP): 2018 Disasters

- After-Action Report/Improvement Plan (AAR/IP): 2019 Makani Pahili 2019 Exercise

## Supporting Training

The following courses will be considered for the HI-EMA Staff, Emergency Management Officers and the State Emergency Response Team (SERT) curriculum.

### Independent Study Courses

| Course Number and Title | Link/Information |
| --- | --- |
| IS-100 Introduction to Incident Command System | http://training.fema.gov/EMIWeb/IS/is100b.asp |
| IS-200 ICS for Single Resources and Initial Action Incidents | http://training.fema.gov/emiweb/is/is200b.asp |
| IS-700 National Incident Management System (NIMS) | http://training.fema.gov/emiweb/is/is700a.asp |
| IS-800 National Response Framework, An Introduction | https://training.fema.gov/is/courseoverview.aspx?code=IS-800.c |
| Professional Development Series (EMI Online) | http://training.fema.gov/is/searchis.aspx?search=PDS |
| IS-546 Continuity of Operations Awareness Course | https://training.fema.gov/is/courseoverview.aspx?code=IS-546.a |
| IS-1300 Introduction to Continuity of Operations | https://training.fema.gov/is/courseoverview.aspx?code=IS-1300 |
| IS-2200 Basic Emergency Operations Center Functions | https://training.fema.gov/IS/courseOverview.aspx?code=IS-2200 |
| IS-908 Emergency Management for Senior Officials | https://training.fema.gov/is/courseoverview.aspx?code=IS-908 |

### Classroom Courses

Classroom courses available that support the development of SERT members

| Course Number and Title | Link/Information |
| --- | --- |
| State Emergency Response Team | www.ready.hawaii.gov |
| WebEOC, Parts I & II | www.ready.hawaii.gov |
| ICS-300 Intermediate ICS for Expanding Incidents | http://training.fema.gov/emicourses/docs/fy16%20catalog.pdf |
| ICS-400 Advanced ICS | http://training.fema.gov/emicourses/docs/fy16%20catalog.pdf |
| MGT-312 Senior Officials Workshop for All-Hazards Preparedness | https://www.ndpc.us/Catalog/TEEXNERRTC/MGT-312 |
| MGT-340 Crisis Leadership and Decision Making | https://www.ndpc.us/Catalog/TEEXNERRTC/MGT-340 |
| MGT-346 Operations and Planning for All Hazards | https://teex.org/Pages/Class.aspx?course=MGT346&courseTitle=EOC+Operations+and+Planning+for+All+Hazards |

## Supporting Exercises

Statewide WebEOC Workshop – Makani Pahili Hurricane Exercise (See Multi-year Training and Exercise Schedule)

Distance Tsunami Drill – (See Multi-year Training and Exercise Schedule)

Local Tsunami Drill – (See Multi-year Training and Exercise Schedule)

Executive Senior Leader Workshop – (See Multi-year Training and Exercise Schedule)

Senior Leader Seminar – Makani Pahili Hurricane Exercise – (See Multi-year Training and Exercise Schedule)

Operations Section Chief Vic Gustafson gives instructions to the State Emergency Response Team at the State Emergency Operations Center. Emergency Support Function representatives from state agencies activated during the multiple disasters in 2018, which included flooding, mudslides and landslides, Kīlauea Volcano’s eruption at the summit and the lower east rift zone on the Big Island and Hurricanes Lane and Olivia. (State of Hawaii photo)

# Mass Care/Logistics and Supply Chain Management

The ability to deliver mass care services will continue to be a top priority for the current training and exercise cycle.  Assumptions contained in the 2015 State of Hawai‘i Catastrophic Hurricane Annex show that mass care support requirements following a major disaster would be extensive. Given Hawaii’s isolation, dependency on imports for critical supplies, reliance on a single hub port and a just-in-time logistics system, the ability to deliver essential mass care services in inexorability linked to logistics and supply chain management.

Training will support stakeholder engagement and understanding of their roles and responsibilities. The formalization of plans and mass care operational coordination structures will be supported by workshops, with a goal of testing plans in more complex exercises as plans are developed.  Sheltering will continue to be a focus, with greater emphasis on post-impact shelters, as well as points of distribution and feeding.

## Rationale for Mass Care/Logistics and Supply Chain Management Focus

- Makani Pahili 2017 Shelter Resourcing Workshop After Action Report/Improvement Plan

- State of Hawai‘i Threat and Hazard Identification and Risk Assessment (2018)

- State of Hawai‘i 2015 Catastrophic Hurricane Annex

- FY18/FY19 Emergency Management Performance Grant

## Supporting Training Courses

The following in-person trainings or workshops are scheduled or planned (see Appendix A):

- L 411 Mass Care/Emergency Assistance for Field Operations

- MGT 319-Medical Countermeasures Points of Dispensing (POD) Planning and Response

- G 418 Mass Care/Emergency Assistance Planning and Ops

- Medical Reserve Corps (MRC) Trainings

- Cardiopulmonary Resuscitation (CPR) Trainings

- County specific POD workshops

The following independent study training courses are available online and will be promoted to stakeholders:

| Independent Study Course Number and Title | Link/Information |
| --- | --- |
| IS-235 Emergency Planning | https://www.training.fema.gov/is/courseoverview.aspx?code=is-235.b |
| IS-405 Overview of Mass Care/Emergency Assistance | - http://training.fema.gov/is/courseoverview.aspx?code=IS-405 |
| IS-26 Guides to Points of Distribution | https://training.fema.gov/is/courseoverview.aspx?code=IS-26 |

The following classroom-based training courses will be promoted to mass care stakeholders:

| Classroom Course Number and Title | Link/Information |
| --- | --- |
| E/L-0411 Mass Care/Emergency Assistance for Field Operations | https://training.fema.gov/emicourses/docs/fy16%20catalog.pdf |
| G-108 Community Mass Care and Emergency Assistance | http://www.nationalmasscarestrategy.org/wp-content/uploads/2014/07/cmcea_factsheet.pdf |
| MGT 319-Medical Countermeasures Points of Dispensing (POD) Planning and Response |  |
| G 418 Mass Care/Emergency Assistance Planning and Ops |  |
| Stop the Bleed trainings | https://www.stopthebleed.org/ |

- Supporting Exercises

The following exercises are scheduled or planned (see Appendix A):

- MP21 POD/Logistic Distribution Management Workshops

- County Points of Distribution (POD) Exercises

- Shelter Activation Drills

# Housing

The training and exercise program will support housing recovery planning. Housing will be the focus of a Pacific Executive Leaders Program (PELP) in 2020 and HI-EMA will hold housing workshops to present lessons learned from the 2018 eruption aimed to drive the development of state and county housing task forces. As the State and County recovery coordination structures are stood-up, HI-EMA will support the creation and delivery of housing focused table-top experiments and exercises. The housing objective is to develop coordination structures and then plans at both the state and county levels.

The State of Hawai’i will work to build its housing recovery capacity by engaging with FEMA, other federal agencies (e.g. the Small Business Administration (SBA), the Department of Housing and Urban Development (HUD)), and non-governmental organizations.

Rationale for Housing Focus

The Kīlauea eruption of 2018 was the first disaster since Hurricane Iniki in 1992, and the first since the release of the National Recovery Framework, that has entailed a prolonged and complicated recovery period. One of the many gaps in the state’s recovery capabilities that the disaster revealed was the lack of readiness to address post-disaster housing, both on a temporary and long-term basis. This capability gap is not unique to Hawai’i and was evident across jurisdictions impacted by catastrophic hurricanes in 2017 and 2018. As a result, FEMA added a requirement into its FY18 and FY19 Emergency Management Performance Grant (EMPG) Program that states should include housing as a component of their training and exercise programs.

Additional documents supporting a focus on Housing include:

- After-Action Report/Improvement Plan (AAR/IP): 2018 Disasters

- State of Hawai‘i Hazard Mitigation Plan (2018)

- State of Hawai‘i Threat and Hazard Identification and Risk Assessment (2018)

- FY18/FY19 Emergency Management Performance Grant

Supporting Training

The following in-person trainings or workshops are scheduled or planned (see Appendix A):

- L-210 Recovery from Disaster: The Local Community Role

- Housing Workshops

The following training courses are available online and will be promoted to stakeholders:

| Independent Study Course Number and Title | Link/Information |
| --- | --- |
| IS-403 Introduction to Individual Assistance | https://training.fema.gov/is/courseoverview.aspx?code=IS-403 |
| IS-772 IA PDA Orientation | https://training.fema.gov/is/courseoverview.aspx?code=IS-772 |
| IS-2900 National Disaster Recovery Framework (NDRF) Overview | https://training.fema.gov/is/courseoverview.aspx?code=IS-2900.a |

The following classroom-based training courses will be promoted to stakeholders:

| Classroom Course Number and Title | Link/Information |
| --- | --- |
| E-0089 NDRS Leadership Workshop |  |
| E/L-209 State Recovery Planning and Coordination |  |
| E/L-210 Recovery from Disaster: The Local Community Role |  |
| E-357 State Individual Assistance Operations |  |

Supporting Exercises

The following exercises are scheduled or planned (see Appendix A):

- Annual Hawaiian Islands Regional Senior Executive Workshop

- Annual State of Hawaii Agencies and Departments Leadership Workshop

- Housing-Specific PELP

- C&C of Honolulu Recovery Tabletop Exercise - (2021 TBD)

- Makani Pahili 21 - Housing Workshop

# Protection Mission Area

## Cybersecurity

The State Office of Homeland Security (OHS) has identified the following priorities related to cybersecurity:

- Implement risk-informed guidelines, regulations, and standards to ensure the security, reliability, integrity, and availability of critical information, records, and communications systems and services through collaborative cybersecurity initiatives and efforts.

- Implement and maintain procedures to detect malicious activity and to conduct technical and investigative-based countermeasures, mitigation and operations against malicious actors to counter existing and emerging cyber-based threats, consistent with established protocols.

- Provide cyber security awareness training and education based on levels of expertise.

- Coordinate with Department of Education/University/Academia to build the cyber resiliency for the state.

- Establish a baseline of current cyber state with critical lifelines critical infrastructure sectors.

- Complete Cyber Security Response Plan.

### Rationale for Cybersecurity Focus

The Framework for Improving Critical Infrastructure Cyber Security stresses the Cyber Security threat exploits the increased complexity and connectivity of critical infrastructure systems thus putting the nation and the state of Hawai‘i’s security, economy and public safety and health at risk.  Presidential Policy Directive PPD-41 provides details for cyber and cyber security.

### Training

Additional trainings for this Core Capability can be found at www.firstrespondertraining.gov/frt/npccatalog

| Course Number and Title | Links |
| --- | --- |
| AWR-136 Essentials of Community Cyber Security | - https://www.firstrespondertraining.gov/frts/npccatalog?id=39 |
| MGT 384 Community Preparedness for Cyber Incident | https://www.firstrespondertraining.gov/frts/npccatalog?id=542 |
| MGT-452 Physical and Cyber Security for Critical Infrastructure | - https://www.firstrespondertraining.gov/frts/npccatalog?id=3322 |

## School Safety

School safety has become a priority for Homeland Security programs.  Those of outside of educations understand there is no greater imperative than keeping students safe.  Hawaii schools are experiencing more threats, and at the same, time more threats are being reported.  The Hawaii State Fusion Center sponsors SafeKekei for reporting incidents.  The schools have processes and procedures, however, staffing in the Security Office is a concern.

The Office of Homeland Security is supporting Department of Education with the STOP Grant with the goal to assist with an intervention program to help prevent an incident and to assist in providing support to youth who portray behavior contrary to school guidelines.

The Office of Homeland Security supports the DOE with their annual Emergency Preparedness Program.

### Training

Additional trainings for this Core Capability can be found at www.firstrespondertraining.gov/frt/npccatalog

| Course Number and Title | Links |
| --- | --- |
| MGT 361 Managing Critical Incidents at Institutions of Higher Learning | https://ndpc.us |
| MGT 467 Sports and Special Events Public Information and Emergency Notification |  |
| MGT 412 Sports Venue Evacuation and Protective Action Course |  |
| Active Shooter Training | - Honolulu Police Department |

## Operational Coordination

The following objectives have been identified in support of Operational Coordination related to homeland security.

- Process for mobilization of resources to support different homeland security scenarios – e.g. active shooter; complex coordinated attack; explosion; vehicle ramming.

- Process for allocating limited resources for events (Chemical, biological, radiological and nuclear defense [CBRNE], canine, etc.)

- Continue support to the responder community with command, control and coordination processes through planning, training, and exercises.

### Rationale for Operational Coordination Focus

The Joint Counterterrorism Awareness Workshop identified several areas of improvement.

### Training and Exercise

Additional training is available at www.firstrespondertraining.gov/frt/npccatalog.

| Course Number and Title | Link |
| --- | --- |
| ISC-300 Intermediate ICS for Expanding Incidents | https://www.eventbrite.com/ |
| ICS-400 Advanced ICS for Command and General Staff |  |
| PER 335 Complex Coordinate Terrorist Attack |  |
| PER 340 Active Threat Integrated Response Course (ATRIC) |  |
| Development of complex coordinated attack tabletop exercise (2020) |  |

## Critical Infrastructure

The prevention and protection of critical infrastructure is a priority for OHS.  Areas requiring attention include but not limited to:

- Update/reassess the Critical Infrastructure Assessments for the State of Hawai‘i.

- Develop countermeasures for systems, networks, assets based on assessment of critical infrastructure.

- Through the Fusion Center identify and assess the threats to state of Hawai‘i; provide materials and products for federal, state, private and public sector for information and steps to assess and reduce risk.

### Rationale for Infrastructure Systems Focus

Identify the lifelines and their criticality to the state and the nation.

### Training

Additional trainings can be found at www.firstrespondertraining.gov/frt/npccatalog.

| Course Number and Title |  | Link |  |
| --- | --- | --- | --- |
| PER-330: Surface Transportation Emergency Preparedness and Security – Mass Transit and Passenger Rail | https://www.eventbrite.com |  |
| MGT-342: Strategic Overview of Disaster Management for Water and Wastewater Utilities |  |  |
| AWR 213 Critical Infrastructure and Resilience Awareness |  |  |

Former Hawaii Emergency Management Agency Administrator Thomas Travis addressing a question/answer during the 2019 Makani Pahili Exercise Statewide Operational Coordination Seminar on June 6, 2019. (State of Hawaii photo)

# Multi-year Training and Exercise Schedule

The Multi-year Training and Exercise Schedule includes emergency management events submitted by agencies and organizations around the state. The details are subject to change. The Hawai‘i Emergency Management Agency also has an online calendar for which agencies and organizations can submit entries http://dod.hawaii.gov/hiema/sert-resources/training-exercise/. Submissions can be e-mailed to Lalo Medina, HI-EMA’s Training Exercise Officer at eulalio.medina@hawaii.gov

|  | ## January 2020 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| DATE | TYPE | CORE CAPABILITIES | EVENT | LOCATION | SPONSOR | CONTACT |
| Jan 07 | TR |  | Media Crisis Communications Training | Ford Island | NOAA | 808-973-5275 |
| Jan 15 | TR |  | WebEOC I | State EOC | HI-EMA | 808-733-4300 |
| Jan 15 | TR |  | Center for Disease Control | Fusion Center | OHS | 808-628-2323 |
| Jan 15 | EX |  | POD Transportation Exercise | Maui | MEMA | 808-270 7285 |
| Jan 16 | EX |  | Table-Top Exercise | USAG-HI EOC, Wheeler Army Air. | USAG-HI | 808-656-0221 |
| Jan 13-17 | EX |  | SNS Transport Full-Scale Exercise | District Health Offices | DOH | 808-587-6569 |
| Jan 14-16 | TR |  | OPSEC Level II MTT | Oahu | IMCOM-P | 808-438-1802 |
| Jan 14-17 | TR |  | Defense Support to Civil Auth. II Crs. | Oahu | PACOM | 808-477-9397 |
| Jan 16 | EX |  | Rail Tabletop Exercise | HART | DEM | 808-723-8965 |
| Jan 17 | EX |  | Kalaupapa Airport Exercise | Maui | MEMA | 808-270 7285 |
| Jan 22 | TR |  | WebEOC II | State EOC | HI-EMA | 808-733-4300 |
| Jan 23 | EX | Housing | Regional Senior Executive Workshop Department Leadership Workshop | HPA, Aloha Tower Campus | NPS/HI-EMA | 808-733-4300 |
| Jan 24 | EX |  | Aerial Photography SAREX | Statewide | CAP | 310-497-3804 |
| Jan 22/29 | TR |  | City Closed Medical POD Training | DEM EOC | DEM | 808-723-8965 |
| Jan 27-31 | TR/EX |  | DDASS Financial Mgmt. Assist. Tng TTX | HING, Kapolei | DCO-E/USARPAC | 808-787-5903 |
| Jan 28-30 | TR |  | Housing-Specific Focused PELP | Oahu | FEMA | 808-851-7900 |
| Jan 29 | TR |  | SERT Orientation | Building 303 | HI-EMA | 808-733-4300 |
| Jan 31-Feb 7 | EX |  | CST Full-Scale Exercise | Maui | MEMA | 808-270 7285 |
| Jan TBD | TR |  | Certification of Hawaii Bomb Squad | TBD | OHS | 808-369-3570 |
| Jan TBD | TR |  | Temporary Power Training | TBD | USACE | 808 835-4721 |
| Jan TBD | TR |  | ICS-300/Intermediate | TBD | DEM | 808-723-8965 |
| Jan TBD | TR |  | EO146 HSEEP Training Course | Hilo EOC | HCCDA | 808-935-0031 |
|  | ## February 2020 |  |  |  |  |  |
| DATE | TYPE | CORE CAPABILITIES | EVENT | LOCATION | SPONSOR | CONTACT |
| Feb 3 | TR |  | AWR 345 Unmanned Aircraft Systems in Disaster Management | Oahu DOD Training Classroom | OHS | 808-369-3570 |
| Feb 3-5 | EX |  | EPLO-DSCA Workshop | TBD | DCO-E | 808-787-0046 |
| Feb 3-7 | TR |  | Crisis and Emergency Risk Communication (CERC) | Hawaii, Kauai, Maui, Oahu | DOH | 808-587-6569 |
| Feb 4 | EX | Critical Transportation | MP20 Debris Management Workshop | Hawaii County | HI-EMA | 808-733-4300 |
| Feb 4-6 | EX |  | Regional Cyber Workshop | Honolulu | FEMA | 808-851-7900 |
| Feb 5 | TR |  | WebEOC I | State EOC | HI-EMA | 808-733-4300 |
| Feb 5 | TR |  | USSS Deep/Dark Net | Fusion Center | OHS | 808-628-2323 |
| Feb 5-6 | TR |  | PER 335 Complex Coordinated Terrorist Attack Training | Hilton | OHS | 808-369-3570 |
| Feb 6 | EX | Critical Transportation | MP20 Debris Management Workshop | Kauai County | HI-EMA | 808-733-4300 |
| Feb 12 | TR |  | WebEOC II | State EOC | HI-EMA | 808-733-4300 |
| Feb 13 | TR |  | HI-EMA Staff Training | State EOC | HI-EMA | 808-733-4300 |
| Feb 19-21 | TR |  | MGT346 EOC Operations & Planning for all Hazards | Maui | OHS | 808-369-3570 |
| Feb 19 | TR |  | WEBEOC/ESF Level III | State EOC | HI-EMA | 808-733-4300 |
| Feb 20 | EX |  | Table-Top Exercise | USAG-HI EOC, Wheeler Army Air | USAG-HI | 808-656-0221 |
| Feb 24-26 | TR |  | MGT346 EOC Operations & Planning for all Hazards | Kauai | OHS | 808-369-3570 |
| Feb 26 | TR |  | 3D | Fusion Center | OHS | 808-628-2323 |
| Feb 27 | EX | Critical Transportation | MP20 Debris Management Workshop | Maui County | HI-EMA | 808-733-4300 |
| Feb 27 | TR |  | HI-EMA Staff Training | State EOC | HI-EMA | 808-733-4300 |
| Feb 26-28 | EX |  | City Closed Medical PODs Exercise | Manoa Valley District Park | DEM | 808-723-8965 |
| TBD | EX | Critical Transportation | Debris Management Workshop | City & County of Honolulu | HI-EMA | 808-733-4300 |
| TBD | TR |  | Honolulu IMT-Situation Unit Leader | TBD | DEM | 808-723-8965 |
| Feb TBD | TR |  | Medical Reserve Corps (MRC) Orientation | Maui | DOH | 808-243-8649 |
| Feb TBD | EX |  | MP20 STAFFEX/H.OPORD Development | State | HING | 808-672-1202 |
| Feb TBD | EX |  | LOADEX | DCO-E | Oahu | 808-787-0046 |
| Feb TBD | TR | TR | MRC CPR Training | HDHO | Hawaii County | 808-974-6010 |
| Feb TBD | TR | TR | Psychologic First Aid | MDHO | Maui County | 808-243-8640 |

|  | ## March 2020 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| DATE | TYPE | CORE CAPABILITIES | EVENT | LOCATION | SPONSOR | CONTACT |
| Mar 2-6 | TR |  | Traditional PELP | Hilo | FEMA | 808-851-7900 |
| Mar 3 | EX | Critical Transportation | MP20 Port Restoration Workshop | Building 303 | HI-EMA | 808-733-4300 |
| Mar 4 | TR |  | WebEOC I | State EOC | HI-EMA | 808-733-4300 |
| Mar 10-11 | TR |  | Incident Command System (ICS-300) | Kauai | OHS | 808-369-3570 |
| Mar 11 | TR |  | WebEOC II | State EOC | HI-EMA | 808-733-4300 |
| Mar 12-13 | TR |  | Incident Command System (ICS-400) | Kauai | OHS | 808-369-3570 |
| Mar 12 | TR |  | HI-EMA Staff Training | State EOC | HI-EMA | 808-733-4300 |
| Mar 18 | TR |  | WEBEOC/ESF Level III | State EOC | HI-EMA | 808-733-4300 |
| Mar 18 | TR |  | DOH Laboratory Response Program | Fusion Center | OHS | 808-628-2323 |
| Mar 18-20 | TR |  | MGT 361 - Managing Critical Incidents at Institutions of Higher Learning | Oahu West Hawaii University | OHS | 808-369-3570 |
| Mar 18-20 | TR |  | MGT455 Radiological Operations Support Specialist Training (ROSS) | City & County/State Oahu | OHS | 808-369-3570 |
| Mar 19 | TR |  | HI-EMA Staff Training | State EOC | HI-EMA | 808-733-4300 |
| Mar 19 | EX |  | Table Top Exercise | Wheeler Army Airfield | USAG-HI | 808-656-0221 |
| Mar 24-25 | TR |  | Incident Command System (ICS-300) | Maui | OHS | 808-369-3570 |
| Mar 26-27 | TR |  | Incident Command System (ICS-400) | Maui | OHS | 808-369-3570 |
| Mar TBD | TR |  | Community Assessment for Public Health Emergency (CASPER) Training | Oahu | DEM/DOH | 808-723-8965 808-587-6569 |
| Mar TBD | TR |  | Honolulu IMT - Operations Sec. Chief | TBD | DEM | 808-723-8965 |
| Mar TBD | TR |  | G0191 EOC/ICS CMD System Interface | Hilo | HCCDA | 808-935-0031 |
| Mar TBD | EX |  | Medical Countermeasure D. Drill | Maui | MDHO | 808-243-8640 |
| Mar TBD | EX |  | Point of Dispensing Tabletop (TTX) | Hawaii | HDHO | 808-974-6010 |
| Mar TBD | EX |  | Extreme Event | Hawaii | HDHO | 808-974-6010 |
| Mar TBD | EX |  | Electronic Call Down Drill | Kauai | DKHO | 808-241-3420 |
| Mar TBD | TR |  | MRC Orientation | Hawaii | HDHO | 808-974-6010 |
| Mar TBD | TR |  | MRC Training | Maui | MDHO | 808-243-8640 |
| Mar TBD | TR |  | Stop the Beed | Oahu | DOH | 808-587-6569 |
| Mar TBD | TR |  | Medical Reserve Corps Orientation | Hawaii | HDHO | 808-974-6010 |
| Mar TBD | TR |  | Points of Distribution (POD) Functional Exercise | Maui | MDHO | 808-243-8640 |
|  | ## April 2020 |  |  |  |  |  |
| DATE | TYPE | CORE CAPABILITIES | EVENT | LOCATION | SPONSOR | CONTACT |
| Apr 1 | TR |  | SERT Orientation (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Apr 1 | TR |  | PER 228 – Advanced Forensics Investigation for Hazardous Environ. | Oahu Aloha Stadium | OHS | 808-369-3570 |
| Apr 1-3 | TR |  | WebEOC I (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Apr 8 | TR |  | FEMA Presentation | Fusion Center | OHS | 808-628-2323 |
| Apr 8 | TR |  | HI-EMA Staff Training (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Apr 9 | TR |  | PER 228 – Advanced Forensics Investigation for Hazardous Environments | Oahu Aloha Stadium | OHS | 808-369-3570 |
| Apr 6-8 | TR |  | MGT 319-Medical Countermeasures Points of Dispensing (POD) Planning and Response | Maui | OHS | 808-369-3570 |
| Apr 13-14 | TR |  | AHIMT Training Course (O-305) | Kauai | OHS | 808-369-3570 |
| Apr 13-17 | EX |  | Distance Tsunami Drill (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Apr 16 | EX |  | Table Top Exercise | EOC, Wheeler Army Airfield | USAG-HI | 808-656-0221 |
| Apr 16 | TR |  | WebEOC II (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Apr 15 | TR |  | MGT 319 - Medical Countermeasures POD Planning and Response | Oahu | OHS | 808-369-3570 |
| Apr 16-17 | EX |  | D14 ADDS, Honolulu 2020 (Drill) | Barbers Point, HI | USCG | 808-535-3306 |
| Apr 22--24 | TR |  | WEBEOC/ESF Level III (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Apr 22 | TR |  | HI-EMA Staff Training (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Apr 23 | TR |  | DOH Disease Investigation Branch | Fusion Center | OHS | 808-628-2323 |
| Apr 29 | EX |  | Kapalua Airport | Maui | DOT-A | 808-838-8702 |
| Apr 30 | TR |  | Honolulu IMT - ICS 400 | TBD | DEM | 808-723-8965 |
| Apr TBD | TR |  | Honolulu IMT – SOFR | TBD | DEM | 808-723-8965 |
| Apr TBD | EX |  | ICS FE Planning P Exercise | Maui | MDHO | 808-243-8640 |
| Apr TBD | TR |  | Points of Distribution (POD) Exercise | Maui | MEMA | 808-270 7285 |

|  | ## May 2020 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DATE |  | TYPE | CORE CAPABILITIES | EVENT | LOCATION | SPONSOR | CONTACT |
| May 2 |  | EX |  | Sector Honolulu SAREX #2 FSE 2020 | Hawaii County | USCG | 808-535-3306 |
| May 5 |  | EX | Critical Transportation | MP20 Debris Management Workshop (Cancelled) | Hawaii County | HI-EMA | 808-733-4300 |
| May 5-6 |  | TR |  | PER-307 Intro to IND Effects and Response Strategies | Oahu | OSH | 808-369-3570 |
| May 6-9 |  | EX |  | D14 Response Trailer, Honolulu 2020 | City & County of Honolulu | USCG | 808-535-3306 |
| May 6 |  | EX | Critical Transportation | MP20 Debris Management Workshop (Cancelled) | Maui County | HI-EMA | 808-733-4300 |
| May 6 |  | TR |  | WebEOC I | State EOC | HI-EMA | 808-733-4300 |
| May 7 |  | EX | Critical Transportation | MP20 Debris Management Workshop (Cancelled) | Kauai County | HI-EMA | 808-733-4300 |
| May 7 |  | TR |  | HI-EMA Staff Training (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| May 12-14 |  | TR |  | Maturing Public Private Partnership Programs | Oahu | OHS | 808-369-3570 |
| May 13 |  | TR |  | WebEOC II (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| May 16 |  | EX |  | Spring Commencement Exercise | University of Hawaii | UH EMO | 808-956-773 |
| May 19 |  | EX | Critical Transportation | MP20 Port Restoration Workshop (Cancelled) | Building 303 | HI-EMA | 808-733-4300 |
| May 20 |  | TR |  | WEBEOC/ESF Level III (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| May 20 (T) |  | TR |  | Hurricane Outlook | TBD | NOAA | 808-973-5275 |
| May 21 |  | TR |  | HI-EMA Staff Training (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| May 21 |  | EX |  | Table Top Exercise | EOC, Wheeler Army Airfield | USAG-HI | 808-656-0221 |
| May TBD |  | EX | Critical Transportation | Debris Management Workshop | City & County of Honolulu | HI-EMA | 808-733-4300 |
| May TBD |  | TR |  | MRC Citizen Preparedness | Hawaii County | HDHO | 808-974-6010 |
| May TBD |  | TR |  | Stop the Bleed | Maui | MDOH | 808-587-6569 |
| May TBD |  | TR |  | Shelter Training | Oahu | DOH & ARC | 808-587-6569 |
| May TBD |  | TR |  | G0775 EOC Management and Ops. | Hilo EOC | HCCDA | 808-935-0031 |
| May TBD |  | TR |  | VIED Search Procedures | Oahu | OHS | 808-369-3570 |
| May TBD |  | TR |  | BMAP | Oahu | OHS | 808-369-3570 |
| May TBD |  | TR |  | Shelter Activation Drill | Kauai | KMRC/ARC | 808-241-3420 |

|  | ## June 2020 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DATE |  | TYPE | CORE CAPABILITIES | EVENT | LOCATION | SPONSOR | CONTACT |
| Jun 3 |  | TR |  | WebEOC I (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Jun 4 |  | EX |  | Active Shooter Full-Scale Exercise | Star of Honolulu | USCG | 808-842-2687 |
| June 9 |  | EX | Situational Assessment | MP 20 Statewide WebEOC Workshop (Cancelled) | Building 303 | HI-EMA | 808-733-4300 |
| Jun 10 |  | EX |  | MP20 Senior Leader Workshop (Cancelled) | TBD | HI-EMA | 808-733-4300 |
| Jun 10 |  | TR |  | CPHC Tropical Storm Outlook | Fusion Center | OHS | 808-628-2323 |
| Jun 8-12/15-17 |  | EX |  | Makani Pahili 2020 Exercise/Support (Cancelled) | State EOC | HING/HI-EMA | 808-733-4300 |
| Jun 17 |  | TR |  | WebEOC II (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Jun 17-19 |  | EX |  | D14 Response Trailer Drill Big Island | Kona, Hawaii County | USCG | 808-535-3306 |
| Jun 18 |  | TR |  | HVX (web-based Hurrevac) | State EOC | HI-EMA | 808-733-4300 |
| Jun 23-24 |  | TR |  | Incident Command System (ICS-300) | Hawaii County | OHS | 808-369-3570 |
| Jun 24 |  | TR |  | WEBEOC/ESF Level III (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Jun 25-26 |  | TR |  | Incident Command System (ICS-400) | Hawaii County | OHS | 808-369-3570 |
| Jun TBD |  | TR |  | Conference: Health and Disaster Impacts of Climate Change | Oahu | DOH | 808-587-6569 |
| Jun TBD |  | TR |  | Psychological First Aid | Oahu | DOH | 808-587-6569 |
| Jun TBD |  | TR |  | Stop the Bleed | Oahu | DOH | 808-587-6569 |
| Jun TBD |  | TR |  | Medical Reserve Corps Orientation | Oahu | DOH | 808-587-6569 |
| Jun TBD |  | TR |  | Emergency Communications | Oahu | OHS | 808-369-3570 |

|  | ## July 2020 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DATE |  | TYPE | CORE CAPABILITIES | EVENT | LOCATION | SPONSOR | CONTACT |
| Jul 1 |  | TR |  | SERT Orientation (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Jul 1-31 |  | EX |  | D14 RIMPAC FSE 2020 | Hawaiian Islands | USCG | 808-535-3306 |
| Jul 7-9 |  | TR | Housing | 210 Recovery from Disaster: The Local Community Role | Oahu | CCSR | 808-768-2277 |
| Jul 8 |  | TR |  | WebEOC I (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Jul 13-17 |  | EX |  | Garrison Full Scale Exercise | Garrison Hawaii | IMCOM-P | 808-438-0611 |
| Jul 15 |  | TR |  | WebEOC II (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Jul 22 |  | TR |  | WEBEOC/ESF Level III (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Jul 27-31 |  | EX |  | CST Exercise | Kauai | KEMA | 808 241-1850 |
| Jul 29-30 |  | TR |  | PER 335 – Complex Coordinated Terrorist Attack | Oahu | OHS | 808-369-3570 |
| Jul TBD |  | TR |  | G0548 COOP Managers Tng. Course | Hilo EOC | HCCDA | 808-935-0031 |
|  | ## August 2020 |  |  |  |  |  |  |
| DATE |  | TYPE | CORE CAPABILITIES | EVENT | LOCATION | SPONSOR | CONTACT |
| Aug 3-4 |  | TR |  | MGT 412 – Sports Venue Evacuation and Protective Action Course | Oahu | OHS | 808-369-3570 |
| Aug 4 |  | EX | Critical Transportation | MP20 Debris Management Workshop (Cancelled) | Hawaii County | HI-EMA | 808-733-4300 |
| Aug 3-4 |  | EX | Critical Transportation | MP20 Debris Management Workshop | Maui County | HI-EMA | 808-733-4300 |
| Aug 5 |  | TR |  | WebEOC I (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Aug 5-6 |  | TR |  | MGT 467 - Sports and Special Events Public Info. & Emergency Notification | Oahu | OHS | 808-369-3570 |
| Aug 6 |  | EX | Critical Transportation | MP20 Debris Management Workshop (Cancelled) | Kauai County | HI-EMA | 808-733-4300 |
| Aug 11-12 |  | TR |  | AWR 136/MGT 384 – Intro to Cyber Security Community Preparedness for Cyber Indicators | Oahu | OHS | 808-369-3570 |
| Aug 12 |  | TR |  | WebEOC II (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Aug 13-14 |  | TR |  | MGT 376 – Physical and Cyber Security and Resilience Awareness Security | Oahu | OHS | 808-369-3570 |
| Aug 18 |  | EX | Critical Transportation | MP20 Port Restoration Workshop | Building 303 | HI-EMA | 808-733-4300 |
| Aug 19 |  | TR |  | WEBEOC/ESF Level III (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Aug TBD |  | EX | Critical Transportation | Debris Management Workshop | City & County of Honolulu | HI-EMA | 808-733-4300 |
| Aug 20 |  | EX |  | Sector Honolulu AMSTEP FE 2020 | Honolulu Harbor | USCG | 808-535-3306 |
| Aug 20 |  | EX |  | Table-Top Exercise | EOC, Wheeler Army Airfield | USAG-HI | 808-656-0221 |
| Aug 25 |  | TR |  | HI-EMA Staff Training | Virtual | HI-EMA | 808-733-4300 |
| Aug TBD |  | TR |  | G-191 Incident Command System/EOC Integration | TBD | DEM | 808-723-8965 |

|  | ## September 2020 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DATE |  | TYPE | CORE CAPABILITIES | EVENT | LOCATION | SPONSOR | CONTACT |
| Sep 2 |  | TR |  | WebEOC I (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Sep 3 |  | TR |  | HI-EMA Staff Training | Virtual | HI-EMA | 808-733-4300 |
| Sep 8 |  | EX | Critical Transportation | MP20 Debris Management Workshop (Cancelled) | Kauai County | HI-EMA | 808-733-4300 |
| Sep 9 |  | TR |  | WebEOC II (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Sep 9-11 |  | TR |  | MGT 323 – Instructor Development Workshop Training | Oahu | OHS | 808-369-3570 |
| Sep 16 |  | TR |  | WEBEOC/ESF Level III (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Sep 22-23 |  | TR |  | Incident Command System (ICS-300) | Oahu | OHS | 808-369-3570 |
| Sep 17 – Oct 8 |  | TR |  | 2020 National Preparedness Symposium | Virtual | FEMA | (301) 447-1000 |
| Sep 24-25 |  | TR |  | Incident Command System (ICS-400) | Oahu | OHS | 808-369-3570 |
| Sep TBD |  | TR |  | Medical Reserve Corps Orientation | Oahu | DOH | 808-587-6569 |
| Sep TBD |  | TR |  | Psychological First Aid | Oahu | DOH | 808-587-6569 |
| Sep TBD |  | TR |  | G-358 Evac. and Re-Entry Planning Crs. | Hilo EOC | HCCDA | 808-935-0031 |
| Sep TBD |  | TR |  | G-358 Evac. and Re-Entry Planning Crs. | Oahu | OHS | 808-369-3570 |
| Sep TBD |  | TR |  | Honolulu IMT - Public Info. Officer | TBD | DEM | 808-723-8965 |

|  | ## October 2020 – December 2020 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DATE |  | TYPE | CORE CAPABILITIES | EVENT | LOCATION | SPONSOR | CONTACT |
| Oct 1 |  | TR |  | SERT Orientation (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Oct 7 |  | TR |  | WebEOC I (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| New Date Jan 12, 2021 |  | EX |  | Training & Exercise Planning Workshop (TEPW) | Building 303 | HI-EMA | 808-733-4300 |
| Oct 14 |  | TR |  | WebEOC II (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Oct 20 |  | EX |  | Local Tsunami Drill Exercise | State EOC | HI-EMA | 808-733-4300 |
| Oct 21 |  | TR |  | WEBEOC/ESF Level III (Cancelled) | State EOC | HI-EMA | 808-733-4300 |
| Oct 31 |  | EX |  | Honolulu Inter. Airport Exercise | Oahu | DOT-A | 808-838-8702 |
| Oct TBD |  | EX |  | Ground Team SAREX | Statewide | CAP | 310-497-3804 |
| Oct TBD |  | TR |  | AWR 213 – Critical Infrastructure and Resilience Awareness Security | Oahu | OHS | 808-369-3570 |
| Oct TBD |  | TR |  | MGT 317 – Disaster Management for Public Services | Oahu | OHS | 808-369-3570 |
| Oct TBD |  | TR |  | PER 330 - Surface Transportation EM Preparedness & Security - Mass Transit & Passenger Rail (STEP-PT) | City & County Honolulu | OHS | 808-369-3570 |
| Oct TBD |  | TR |  | PER 331 - Surface Transportation EM Preparedness & Security - Senior Officials (STEP-SR) | City & County Honolulu | OHS | 808-369-3570 |
| Oct TBD |  | TR |  | Honolulu IMT - ICS 300 | TBD | DEM | 808-723-8965 |
| Nov 4 |  | TR |  | WebEOC I | State EOC | HI-EMA | 808-733-4300 |
| Nov 4 |  | EX | Critical Transportation | MP20 Debris Management Workshop | Hawaii County | HI-EMA | 808-733-4300 |
| Nov 5 |  | EX | Critical Transportation | MP20 Debris Management Workshop | Maui County | HI-EMA | 808-733-4300 |
| Nov 6 |  | EX | Critical Transportation | MP20 Debris Management Workshop | Kauai County | HI-EMA | 808-733-4300 |
| Nov 17 |  | EX | Critical Transportation | MP20 Port Restoration Workshop | Building 303 | HI-EMA | 808-733-4300 |
| Nov 18 |  | TR |  | WebEOC II | State EOC | HI-EMA | 808-733-4300 |
| Nov 25 |  | TR |  | WEBEOC/ESF Level III | State EOC | HI-EMA | 808-733-4300 |
| Nov 30 |  | EX |  | Kona Airport Exercise | Hawaii County | DOT-A | 808-838-8702 |
| Nov TBD |  | EX | Critical Transportation | Debris Management Workshop | City & County of Honolulu | HI-EMA | 808-733-4300 |
| Nov TBD |  | TR |  | Stop the Bleed | Oahu | DOH | 808-587-6569 |
| Nov TBD |  | TR |  | G0418 Mass Care/Emergency Assistance Planning and Ops. | Hilo EOC | HCCDA | 808-935-0031 |
| Nov TBD |  | TR |  | G0418 Mass Care/Emergency Assistance Planning and Ops. | Oahu | OHS | 808-369-3570 |
| Nov TBD |  | TR |  | Honolulu IMT - O-305 Course | TBD | DEM | 808-723-8965 |
| Nov TBD |  | TR |  | Honolulu IMT - Honolulu Marathon Exercise | TBD | DEM | 808-723-8965 |
| Dec 2 |  | TR |  | WebEOC I | State EOC | HI-EMA | 808-733-4300 |
| Dec 8 |  | EX | Critical Transportation | MP20 Debris Management TTX | Building 303 | HI-EMA | 808-733-4300 |
| Dec 9 |  | TR |  | WebEOC II | State EOC | HI-EMA | 808-733-4300 |
| Dec 15 |  | EX | Critical Transportation | MP20 Port Restoration TTX | Building 303 | HI-EMA | 808-733-4300 |
| Dec 16 |  | TR |  | WEBEOC/ESF Level III | State EOC | HI-EMA | 808-733-4300 |
| Dec 19 |  | EX |  | Spring Commencement Exercise | University of Hawaii | UH EMO | 808-956-773 |
| Dec TBD |  | TR |  | Medical Reserve Corps Orientation | Oahu | DOH | 808-587-6569 |
| TBD |  | EX |  | National Level Exercise 2020 | State | FEMA | 808-851-7906 |

|  | ## January 2021 – December 2021 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DATE |  | TYPE | CORE CAPABILITIES | EVENT | LOCATION | SPONSOR | CONTACT |
| Jan 12 |  | EX | Planning | TEPW Training & Exercise Planning Workshop (TEPW) | State | HI-EMA | 808-733-4300 |
| Jan 27 |  | TR |  | SERT Orientation | State EOC | HI-EMA | 808-733-4300 |
| Jan TBD |  | EX | Critical Transportation | MP21 Port Restoration Workshop | Hawaii County | HI-EMA | 808-733-4300 |
| Jan TBD |  | EX | Critical Transportation | MP21 Port Restoration Workshop | Maui County | HI-EMA | 808-733-4300 |
| Jan TBD |  | EX | Critical Transportation | MP21 Port Restoration Workshop | Kauai County | HI-EMA | 808-733-4300 |
| Jan TBD |  | EX | Critical Transportation | MP21 Port Restoration Workshop | C&C of Honolulu | HI-EMA | 808-733-4300 |
| Jan 29 |  | EX | Logistics and Supply Chain Management | MP21 POD/Logistic Distribution Management Workshop | State | HI-EMA | 808-733-4300 |
| Apr 7 |  | TR |  | SERT Orientation | State EOC | HI-EMA | 808-733-4300 |
| Apr 15 |  | EX |  | Distance Tsunami Drill | State EOC | HI-EMA | 808-733-4300 |
| Apr TBD |  | EX | Critical Transportation | MP21 Port Restoration Workshop | Hawaii County | HI-EMA | 808-733-4300 |
| Apr TBD |  | EX | Critical Transportation | MP21 Port Restoration Workshop | Maui County | HI-EMA | 808-733-4300 |
| Apr TBD |  | EX | Critical Transportation | MP21 Port Restoration Workshop | Kauai County | HI-EMA | 808-733-4300 |
| Apr TBD |  | EX | Critical Transportation | MP21 Port Restoration Workshop | C&C of Honolulu | HI-EMA | 808-733-4300 |
| Apr 09 |  | EX | Logistics and Supply Chain Management | MP21 POD/Logistic Distribution Management Workshop | State | HI-EMA | 808-733-4300 |
| May 11-15 |  | EX | Operational Coordination | Makani Pahili 2021 Exercise | State | HI-EMA | 808-733-4300 |
| May 11 |  |  | Logistics and Supply Chain Management | MP21 Temporary Power TTX | State | HI-EMA | 808-733-4300 |
| May 13 |  |  | Housing | MP21 Housing Workshop | State | HI-EMA | 808-733-4300 |
| May 14 |  | EX |  | MP21 Senior Leader Executive Seminar | State | HI-EMA | 808-733-4300 |
| Jul 12-17 |  | EX |  | VG21 Van Guard Full-Scale Exercise | State | HING | 808-672-1202 |
| Jul TBD |  | EX | Critical Transportation | MP21 Port Restoration Workshop | Hawaii County | HI-EMA | 808-733-4300 |
| Jul TBD |  | EX | Critical Transportation | MP21 Port Restoration Workshop | Maui County | HI-EMA | 808-733-4300 |
| Jul TBD |  | EX | Critical Transportation | MP21 Port Restoration Workshop | Kauai County | HI-EMA | 808-733-4300 |
| Jul TBD |  | EX | Critical Transportation | MP21 Port Restoration Workshop | C&C of Honolulu | HI-EMA | 808-733-4300 |
| Jul 09 |  | EX | Logistics and Supply Chain Management | MP21 POD/Logistic Distribution Management Workshop | State | HI-EMA | 808-733-4300 |
| Jul 7 |  | TR |  | SERT Orientation | State EOC | HI-EMA | 808-733-4300 |
| Sep 30 |  | EX |  | Kahului Airport Exercise | Maui | DOT-A | 808-838-8702 |
| Oct 6 |  | TR |  | SERT Orientation | State EOC | HI-EMA | 808-733-4300 |
| Oct 21 |  | EX |  | Local Tsunami Drill | State | HI-EMA | 808-733-4300 |
| Oct TBD |  | EX | Critical Transportation | MP21 Port Restoration Workshop | Hawaii County | HI-EMA | 808-733-4300 |
| Oct TBD |  | EX | Critical Transportation | MP21 Port Restoration Workshop | Maui County | HI-EMA | 808-733-4300 |
| Oct TBD |  | EX | Critical Transportation | MP21 Port Restoration Workshop | Kauai County | HI-EMA | 808-733-4300 |
| Oct TBD |  | EX | Critical Transportation | MP21 Port Restoration Workshop | C&C of Honolulu | HI-EMA | 808-733-4300 |
| Oct 11 |  | EX | Logistics and Supply Chain Management | MP21 POD/Logistic Distribution Management Workshop | State | HI-EMA | 808-733-4300 |
| Dec 08 |  | EX | Critical Transportation | MP21 Port Restoration TTX | Building 303 | HI-EMA | 808-733-4300 |
| Dec 16 |  | EX | Logistics and Supply Chain Management | MP21 POD/Logistic Distribution Management TTX | State | HI-EMA | 808-733-4300 |

|  | ## January 2022 – December 2022 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DATE |  | TYPE | CORE CAPABILITIES | EVENT | LOCATION | SPONSOR | CONTACT |
| Jan 11 |  | EX | Planning | TEPW Training & Exercise Planning Workshop (TEPW) | State | HI-EMA | 808-733-4300 |
| Jan 26 |  | TR |  | SERT Orientation | State EOC | HI-EMA | 808-733-4300 |
| Jan TBD |  | EX | Housing | MP22 Housing Workshop | Hawaii County | HI-EMA | 808-733-4300 |
| Jan TBD |  | EX | Housing | MP22 Housing Workshop | Maui County | HI-EMA | 808-733-4300 |
| Jan TBD |  | EX | Housing | MP22 Housing Workshop | Kauai County | HI-EMA | 808-733-4300 |
| Jan TBD |  | EX | Housing | MP22 Housing Workshop | C&C of Honolulu | HI-EMA | 808-733-4300 |
| Apr 6 |  | TR |  | SERT Orientation | State EOC | HI-EMA | 808-733-4300 |
| Apr 14 |  | EX | Operational Coordination | Distance Tsunami Drill | State EOC | HI-EMA | 808-733-4300 |
| Apr TBD |  | EX | Housing | MP22 Housing Workshop | Hawaii County | HI-EMA | 808-733-4300 |
| Apr TBD |  | EX | Housing | MP22 Housing Workshop | Maui County | HI-EMA | 808-733-4300 |
| Apr TBD |  | EX | Housing | MP22 Housing Workshop | Kauai County | HI-EMA | 808-733-4300 |
| Apr TBD |  | EX | Housing | MP22 Housing Workshop | C&C of Honolulu | HI-EMA | 808-733-4300 |
| May 09-13 |  | EX | Operational Coordination | Makani Pahili 2021 Exercise | State | HI-EMA | 808-733-4300 |
| May 14 |  | EX | Planning | MP22 Senior Leader Executive Seminar | State | HI-EMA | 808-733-4300 |
| Jul TBD |  | EX | Housing | MP22 Housing Workshop | Hawaii County | HI-EMA | 808-733-4300 |
| Jul TBD |  | EX | Housing | MP22 Housing Workshop | Maui County | HI-EMA | 808-733-4300 |
| Jul TBD |  | EX | Housing | MP22 Housing Workshop | Kauai County | HI-EMA | 808-733-4300 |
| Jul TBD |  | EX | Housing | MP22 Housing Workshop | C&C of Honolulu | HI-EMA | 808-733-4300 |
| Jul 09 |  | EX | Logistics and Supply Chain Management | MP21 POD/Logistic Distribution Management Workshop | State | HI-EMA | 808-733-4300 |
| Jul 7 |  | TR |  | SERT Orientation | State EOC | HI-EMA | 808-733-4300 |
| Oct 6 |  | TR |  | SERT Orientation | State EOC | HI-EMA | 808-733-4300 |
| Oct 20 |  | EX | Operational Coordination | Local Tsunami Drill | State | HI-EMA | 808-733-4300 |
| Oct TBD |  | EX | Housing | MP22 Housing Workshop | Hawaii County | HI-EMA | 808-733-4300 |
| Oct TBD |  | EX | Housing | MP22 Housing Workshop | Maui County | HI-EMA | 808-733-4300 |
| Oct TBD |  | EX | Housing | MP22 Housing Workshop | Kauai County | HI-EMA | 808-733-4300 |
| Oct TBD |  | EX | Housing | MP22 Housing Workshop | C&C of Honolulu | HI-EMA | 808-733-4300 |
| Dec 08 |  | EX | Housing | MP22 Housing Workshop | Building 303 | HI-EMA | 808-733-4300 |

# Acknowledgements

| Hosts Hawai‘i Emergency Management Agency State of Hawai‘i Homeland Security Office Counties Hawai‘i County Civil Defense Agency City and County of Honolulu Department of Emergency Management Maui Emergency Management Agency Kaua‘i Emergency Management Agency State of Hawai‘i Department of Accounting and General Services Department of Accounting and General Services - ASO Department of Accounting and General Services - ETS Department of Accounting and General Services - Public Works Department of Agriculture Department of Budget and Finance Department of Business, Economic Development & Tourism - State Energy Office Department of Commerce and Consumer Affairs | Department of Defense Department of Health Department of Human Resources Development Department of Human Services Department of Human Services - Benefit, Employment and Support Services Division Department of Human Services - Hawai‘i Public Housing Authority Department of Land and Natural Resources - Division of Forestry and Wildlife Department of Public Safety Department of Transportation Governor's Office Hawai‘i Air National Guard 201 Air Operations Unit Hawai‘i National Guard Hawai‘i Radio Amateur Civil Emergency Services Hawai‘i State Fusion Center Hawai‘i State Public Library System Public Utilities Commission State Procurement Office University of Hawai‘i | Federal/Military Federal Emergency Management Agency 9th Mission Support Command (Army Reserve) 201st Air Operations Group /HIANG Civil Air Patrol Defense Coordinating Element NOAA National Weather Service Pearl Harbor Defense Logistics Agency Pearl Harbor Naval Shipyard U.S. Coast Guard District 14 U.S. Indo-Pacific Command U.S. Army Pacific Command Private Industry, Non-Profit Agencies, Nongovernmental Agencies American Amateur Radio Club American Red Cross Chaminade University of Honolulu Hawai‘i Voluntary Organizations Active in Disasters Hawaii Healthcare Emergency Management Coalition Hawaiian Airlines Hawaiian Electric Companies Delta Airlines |
| --- | --- | --- |

# Maintenance Section

The Training and Exercise Plan (TEP) is a living document owned by HI-EMA Preparedness Branch that will be updated and refined annually. The plan covers the overall training and exercise program priorities for a three-year period, with the acknowledgment that priorities may be adjusted to address changing circumstances.