## CONTRACT
Project Manager checklist/reminders
All items may not be applicable for each project.
CRF
Prepare CRF for initial project or supplement - If supplement list CA# and Supplement #
Provide project title and brief description
Identify complete funding code line(s) - Verify all funding with FM & Fiscal
Attach SOW & drawings to CRF
Identify wage rates (verify w/ State Personnel) if required
Identify special requirements
List licenses required if any
Identify Pre-Bid requirement (see Posting & Pre-Bid)
Is a RECS (Request for Exemption of Contractual Services) required? If so, attach copy.
Submit CRF, SOW, drawings and RECS to Contracts Assistant via email.
POSTING & PRE-BID
Pre-Bid Conference is required for IFB jobs estimated over $500K & RFP jobs estimated over $100K. If a Pre-Bid is requried coordinate date with CA prior to posting of notice (must be posted in notice) Set-up Pre-Bid conference approx. (2) weeks after posting. Get dates from CA
Notify Fund Manager to attend if needed
Notify Project Designer to attend if applicable
If a Pre-Bid conference is not required but you wish to offer a site visit, coordinate with the CA the same as above. The Fund manager is not required to attend a site visit.
Assist CA with Q&A from Pre-Bid or site visit for Addendum posting
BID OPENING & CONTRACT COMPLETION
Attend bid opening & sign as witness
Receive Award letter
Receive copy of completed contract or supplement
PRE-CON MEETING
Set-up pre-con meeting, coord with CA
Notify Contractor to attend
Notify Facility POC/AFA to attend
PM to run meeting, handle sign in, agenda and take minutes.
Send out via e-mail pre-con minutes & attendance sheet to all attendees and CA
Received copy of NTP
DURING CONTRACT
Monitor progress of contract & ensure vendor is adhereing to all contract conditions.
Are Act 68 & Act 17 forms required? Submitted?
Verify certified payroll if required.
REQUIREMENTS FOR FINAL PAYMENT
Final inspection Completed by PM.
PM receives final invoice.
PM to confirm via email with CA if Act 68 and Act 17 forms have been submitted prior to submitting invoice for final payment for ALL construction projects as required.
Receive email from CA if Act 68 & Act 17 forms are received.
If forms are not received: Received copy of Withholding of Payment letter
Receive "Authorization to Proceed with Final Payment" letter from CA
PM submits invoice for final payment along with Authorization to Proceed with Final Payment letter to Fiscal to process final payment and close the contract.
SUPPLEMENT
CRF
Is the CA# listed? What is the Supplement #?
Provide project title and brief description
Identify complete funding code line(s). Verify with FM & Fiscal.
Attach SOW and drawings
Identify wage rates (Verify with State personnel) If required
Identify special requirements
List licenses required if any
Is a RECS (Request for Exemption of Contractual Services) required? If so, attach copy.
Submit CRF, SOW and drawings to Contracts Assistant
Received completed copy of supplement